## Activity List
PROJECT NAME
WBS # | Activty | Duration in Days | Cost | Start | Finish | Resource | Predecessor | Hints
1 | Initation and Planning | [6 empty] | Though there are many ways to create an activity list, study this and understand how it is organized. It reflects many common practices.
1.1 | Project Initiation | [6 empty] | Map the duration and cost estimates from the three point estimate tab
1.1.1 | Identify stakeholders | 2 | 252.395 | 2023-12-04 | 2023-12-05 | Project Manager |  | A common convention is to use row fill colors to identify phases, deliverables, or work packages
1.1.2 | Identify project requirements | 15 | 771.84 | 2023-12-06 | 2023-12-26 | Business Analyst |  | Note how each level of breakdown adds 1 decimal point to the WBS #
1.1.3 | Perform Gap and SWOT analysis | 4 | 344.175 | 2023-12-27 | 2023-01-02 | Project Manager
1.1.4 | Create project charter | 5 | 458.9 | 2023-01-03 | 2023-01-09 | Project Manager
1.1.5 | Review project charter | 2 | 257.05 | 2023-01-10 | 2023-01-11 | Sponsor |  | Another common convention is to indent 1 level for each level of breakdown
1.1.6 | Charter approval | 0 | 179.935 |  |  | Sponsor |  | Use zero duration tasks to indicate milestones. Milestones can indicate the end of a phase, gate review, or approval of a deliverable
1.2 | Project Planning | [6 empty] | Do assign a duration to a review activity, though.
1.2.1 | Create WBS | 7 | 481.845 | 2023-01-12 | 2023-01-20 | Project Manager |  | This list gets updated continuously throughout planning and execution
1.2.2 | Create schedule | 5 | 504.79 | 2023-01-23 | 2023-01-27 | Project Manager |  | PM software will visualize this as a Gantt chart
1.2.1.1 | Create duration estimates | 4 | 289.08 | 2023-01-30 | 2023-02-02 | Project Team
1.2.2.3 | Sequence tasks | 3 | 208.78 | 2023-02-07 | 2023-02-09 | Project Team
1.2.2.4 | Identify critical path | 2 | 273.02 | 2023-02-10 | 2023-02-13 | Project Team
1.2.3 | Create budget plan | 3 | 435.955 | 2023-02-14 | 2023-02-16 | Project Manager
1.2.4 | Create project risk management plan | 2 | 458.9 | 2023-02-17 | 2023-02-20 | Project Manager
1.2.5 | Create communications plan | 3 | 344.175 | 2023-02-21 | 2023-02-23 | Project Manager
1.2.6 | Create quality plan | 2 | 390.065 | 2023-02-24 | 2023-02-27 | Project Manager
1.2.7 | Review project plans | 2 | 334.165 | 2023-02-28 | 2023-03-01 | Sponsor
1.2.8 | GATE REVIEW: Approve Project Plans | 0 | 102.82 |  |  | Sponsor
2 | Project Execution
2.1 | Deliverable 1
2.1.1 | UX design prototype | 10 | 442.395 | 2023-03-02 | 2023-03-15 | UX Team
2.1.2 | Review UX design | 2 | 666.33 | 2023-03-16 | 2023-03-17 | UX team and Stakeholders
2.1.3 | Deliverable 1 approval | 0 | 385.77 |  |  | UX team and Stakeholders
2.2 | Deliverable 2
2.2.1 | Code development for front end | 90 | 6263.82 | 2023-03-20 | 2023-07-14 | Development Team
2.2.2 | Code development for backend | 60 | 5356.02 | 2023-07-03 | 2023-09-22 | Development Team
2.2.3 | Unit testing | 7 | 635.46 | 2023-09-25 | 2023-10-03 | Development Team
2.2.4 | Integration testing | 15 | 1270.92 | 2023-10-04 | 2023-10-24 | Development Team
2.4.5 | Deliverable 2 approval | 0 | 435.955 |  |  | Project Manager
2.3 | Deliverable 3
2.3.1 | System testing | 30 | 794.76 | 2023-10-25 | 2023-12-07 | Quality Control Team
2.3.2 | Load Testing | 10 | 687.36 | 2023-12-08 | 2023-12-21 | Quality Control Team
2.3.3 | Regression Testing | 12 | 440.34 | 2023-12-22 | 2024-01-10 | Quality Control Team
2.3.4 | User Acceptance Testing | 10 | 1382.29 | 2024-01-11 | 2024-01-24 | Product Owner
2.3.5 | Deployment to production environment | 7 | 317.73 | 2024-01-25 | 2024-02-02 | Devops Team
2.3.6 | Deliverable 3 approval | 0 | 596.57 |  |  | Project Manager
3 | Project Closure
3.1 | Accept each deliverable | 5 | 434.175 | 2024-02-05 | 2024-02-09 | Internal and External Stakeholder
3.2 | Conduct lessons learned | 5 | 321.2 | 2024-02-12 | 2024-02-16 | Project Manager
3.3 | Create project archive | 5 | 176.66 | 2024-02-19 | 2024-02-23 | Project Manager
3.4 | Sponsor review | 6 | 411.28 | 2024-02-26 | 2024-02-26 | Sponsor
3.5 | GATE REVIEW: Project approval and closure | 0 | 649.87 |  |  | Executive and External Stakeholder

## Resource Requirements
Activity Resource Requirements
Role (Differentiate Jr, Mid, Sr Level) | Required Skills | Total Resource Hours Needed | Number FTE Required | Resource Acuisition Strategy | Labor Rate
PM | Project planning ,Team management, Goal setting, Relevant technical skills. Proofreading, Writing, Negotiation, Schedule planning. | 1720 | 0.82692 | Borrower | 45.89
Business Analyst | Process Mapping,Product Innovation & Improvement,Business Transformation IT-Business Alignment,Business Process Improvement,Project Management & Prioritization Metric Development | 600 | 0.28846 | Borrower | 42.88
Sponsor | Leadership, Management, Initiation Duties, Closing Duties, Consulting | 400 | 0.19231 | Internal | 51.41
Project Team | Scheduling, Estimation, Task management, and Basic analytics, Reporting | 360 | 0.17308 | Internal | 32.12
UX Team | Wireframing and prototyping, UX writing, Visual communication and UI,User testing | 480 | 0.23077 | Borrower | 30.51
Development Team | Programming Skills, Database management, Version Conrol, API Development, Software Architure,Web Development | 6800 | 3.2692 | Borrower | 60.52
Quality Control Team | Database, Calibration,Customer Service,Troubleshooting Quality assurance Tool | 2080 | 1 | Borrower | 21.48
Product Owner | Product Vision, User Centric Focus, Prioritization, Backlog Management, Product Roadmap,Release Planning,Leadership | 400 | 0.19231 | Internal | 56.42
Devops Team | Scripting and Coding,Version Control,Continuous Integration (CI),Continuous Deployment (CD),Infrastructure as Code (IaC),Containerization,Cloud Platforms | 280 | 0.13462 | Borrower | 30.26
Comments
This is hard to do in a spreadsheet. Project Management software makes this much easier!
This has to be developed progressively - First allocate resources to activities on the activity list - After you create duration estimates, sum the total of hours per resource type - Make sure you do not overallocate your resources' capacity (hours/day, hours/week, or have total hours > than the project duration) - When you exceed the capacity of a resource, add more, assign most difficult work to most skilled resources - You may have to negotiate for more resources or clearly identify the resource constraints to. your sponsor
Acquisition strategy - "Internal" - use resources controlled by your sponsor or stakeholders - "Borrow" - negotiate for internal resources not controlled by your sponsor or stakeholders - New hire - Outsource
Labor rate - For internal resources, get "loaded" rate from HR - Use actual labor rate for outsourced resources

## Cost 3 Point Estimate
Estimates for Duration and Costs
WBS # | Activity | Resource | Labor Rate | Duration Estimates |  |  | 3 Point Estimates
|  |  |  | Worst Case Estimate | Most Likely Estimate | Best Case Estimate | 3 Point Duration Estimate | Rounded Hours | 3 Point Cost Estimate
1 | Initation and Planning | [7 empty] | 0
1.1 | Project Initiation | [7 empty] | 0
1.1.1 | Identify stakeholders | Project Manager | 45.89 | 10 | 5 | 2 | 5.3333 | 5.5 | 252.395
1.1.2 | Identify project requirements | Business Analyst | 42.88 | 20 | 18 | 15 | 17.8333 | 18 | 771.84
1.1.3 | Perform Gap and SWOT analysis | Project Manager | 45.89 | 12 | 7 | 4 | 7.3333 | 7.5 | 344.175
1.1.4 | Create create project charter | Project Manager | 45.89 | 15 | 10 | 5 | 10 | 10 | 458.9
1.1.5 | Review project charter | Sponsor | 51.41 | 8 | 5 | 2 | 5 | 5 | 257.05
1.1.6 | Charter approval | Sponsor | 51.41 | 8 | 3 | 0 | 3.3333 | 3.5 | 179.935
1.2 | Project Planning | [7 empty] | 0
1.2.1 | Create WBS | Project Manager | 45.89 | 15 | 10 | 7 | 10.3333 | 10.5 | 481.845
1.2.2 | Create schedule | Project Manager | 45.89 | 21 | 10 | 5 | 11 | 11 | 504.79
1.2.1.1 | Create duration estimates | Project Team | 32.12 | 18 | 8 | 4 | 9 | 9 | 289.08
1.2.2.3 | Sequence tasks | Project Team | 32.12 | 15 | 5 | 3 | 6.3333 | 6.5 | 208.78
1.2.2.4 | Identify critical path | Project Team | 32.12 | 20 | 7 | 2 | 8.3333 | 8.5 | 273.02
1.2.3 | Create budget plan | Project Manager | 45.89 | 30 | 6 | 3 | 9.5 | 9.5 | 435.955
1.2.4 | Create project risk management plan | Project Manager | 45.89 | 40 | 4 | 2 | 9.6667 | 10 | 458.9
1.2.5 | Create communications plan | Project Manager | 45.89 | 20 | 5 | 3 | 7.1667 | 7.5 | 344.175
1.2.6 | Create quality plan | Project Manager | 45.89 | 25 | 6 | 2 | 8.5 | 8.5 | 390.065
1.2.7 | Review project plans | Sponsor | 51.41 | 15 | 5 | 2 | 6.1667 | 6.5 | 334.165
1.2.8 | GATE REVIEW: Approve Project Plans | Sponsor | 51.41 | 4 | 2 | 0 | 2 | 2 | 102.82
2 | Project Execution | [7 empty] | 0
2.1 | Deliverable 1 | [7 empty] | 0
2.1.1 | UX design prototype | UX Team | 30.51 | 21 | 14 | 10 | 14.5 | 14.5 | 442.395
2.1.2 | Review UX design | Stakeholder | 70.14 | 15 | 10 | 2 | 9.5 | 9.5 | 666.33
2.1.3 | Deliverable 1 approval | Stakeholder | 70.14 | 9 | 6 | 0 | 5.5 | 5.5 | 385.77
2.2 | Deliverable 2 | [7 empty] | 0
2.2.1 | Code development for front end | Development team | 60.52 | 130 | 100 | 90 | 103.3333 | 103.5 | 6263.82
2.2.2 | Code development for backend | Development team | 60.52 | 110 | 90 | 60 | 88.3333 | 88.5 | 5356.02
2.2.3 | Unit testing | Development team | 60.52 | 15 | 10 | 7 | 10.3333 | 10.5 | 635.46
2.2.4 | Integration testing | Development team | 60.52 | 30 | 20 | 15 | 20.8333 | 21 | 1270.92
2.4.5 | Deliverable 2 approval | Project Manager | 45.89 | 15 | 10 | 0 | 9.1667 | 9.5 | 435.955
2.3 | Deliverable 3 | [7 empty] | 0
2.3.1 | System testing | Quality Control Team | 21.48 | 50 | 35 | 30 | 36.6667 | 37 | 794.76
2.3.2 | Load Testing | Quality Control Team | 21.48 | 60 | 30 | 10 | 31.6667 | 32 | 687.36
2.3.3 | Regression Testing | Quality Control Team | 21.48 | 30 | 20 | 12 | 20.3333 | 20.5 | 440.34
2.3.4 | User Acceptance Testing | Product Owner | 56.42 | 35 | 25 | 10 | 24.1667 | 24.5 | 1382.29
2.3.5 | Deployment to production environment | Devops Team | 30.26 | 15 | 10 | 7 | 10.3333 | 10.5 | 317.73
2.3.6 | Deliverable 3 approval | Project Manager | 45.89 | 21 | 14 | 0 | 12.8333 | 13 | 596.57
3 | Project Closure | [7 empty] | 0
3.1 | Accept each deliverable | Internal and External Stakeholder | 57.89 | 12 | 7 | 5 | 7.5 | 7.5 | 434.175
3.2 | Conduct lessons learned | Project Team | 32.12 | 15 | 10 | 5 | 10 | 10 | 321.2
3.3 | Create project archive | Project Team | 32.12 | 8 | 5 | 5 | 5.5 | 5.5 | 176.66
3.4 | Sponsor review | Sponsor | 51.41 | 12 | 7 | 6 | 7.6667 | 8 | 411.28
3.5 | GATE REVIEW: Project approval and closure | Executive and External Stakeholder | 99.98 | 10 | 7 | 0 | 6.3333 | 6.5 | 649.87
[7 empty] | Labor Subtotal |  | 27756.795
[7 empty] | Project Labor Overhead 20% |  | 5551.359
Create the 3 Point Estimate | [6 empty] | Labor Total |  | 33308.154
1. Populate WBS # and Activity Name.
2. Reference the labor rate from the resource requirements tab.
3. Enter the worst case, most likely, best case scenarios.
4. Calculate the 3 point estimate using the formula below.
5. Round the 3 point estimate to the nearest 1/2 hour. (You may round as appropriate for your project).
6. Sum the cost of all labor estimates to create a subtotal.
7. Add 20% to the subtotal to account for project labor overhead costs.
8. Sum the labor subtotal + overhead to get labor total
9. Map the labor estimate to the budget overview tab.
10. Map the activity duration to your activity list.
11. Map the 3 point estimate to your activity list.
Three point estimate Formula
= ((Worst) + 4(Most Likely) + (Best))/6
Hints
- Check the formulas in columns H6, I6, J6, J16, J17, J18
- Format numbers to 2 decimals for currency.
- Reference rates from the resource requirements tab.
- Use cell references whenever possible to avoid entering data twice, creating out of sync data
Note
You need to understand the relationship between duration, labor rate, and cost of activity
PM software will calculate the cost of activities based on inputs you give re. duration, labor rate, and who is allocated to the activity
Addiing 20% overhead helps you account for things like meetings and email that are not captured on the activity list and help you avoid overallocating resources
Another way of thinking about this is that you only want to allocate 80% of a resources time to work on the activity list. For a normal work week, that = 32 hours per week
Another consideration: If a resource is juggling many different activities at once, they become less efficient and more likely to make mistakes. Try to keep the number of activities to a minimum.

## Material Costs
Material & Service Costs
Item | Budgeted amount
Material Costs:
Software Licenses | 10000
Hardware Upgrades | 5000
Training Materials | 2000
Office Supplies | 500
Project-Specific Tools | 3000
Service Costs:
Consultancy Services | 15000
Maintenance Services | 8000
Training Services | 4000
Cloud Services | 2500
Integration Services | 6000
Total: | 56000
Enter all material and service costs
Sum material and service costs
Map total to budget overview

## Budget
Budget Overview
Item | Budgeted amount
Internal labor costs | 33308.154
Outsourced labor costs | 0
Material costs | 20500
Service costs | 35500
Contingency Reserve Budget | 43200
Subtotal | 132508.154
Mgmt reserve 10% | 13250.8154
Total: | 145758.9694
Create the Budget Overview
Enter most up to date estimates for labor, materials, and services
Add the contingency reserve from your risk register
Add 10% to your subtotal for your management reserve

## Risk Register
Risk Register
Risk Identification |  |  | Qualitative Risk Analysis |  | Quantitative Risk Analysis |  |  |  |  | Risk Response Planning
Risk # | Risk Name | Risk Statement | Likelihood - Impact | Risk Rank | Likelihood % | Impact Time | Scehdule Risk | Impact $ | Cost Risk (EMV) | Risk Strategy | Mitigation Strategy
R1.1 | Scope Creep | Scope creep can lead to increased project complexity, delays, and additional work. | Moderate - High | 3 | 50% | Mid-project | Yes | 20000 | 10000 | Avoidance | Define and freeze scope, change control process.
R1.2 | Market Changes | Changes to the project may be necessary due to shifting consumer requests or market conditions. | Moderate - Moderate | 2 | 30% | Throughout | Yes | 12000 | 3600 | Adaptation | Regular market analysis, agility in product design.
R1.3 | Technology Challenges | Complex technical requirements | Low - High | 2 | 20% | Early-project | No | 5000 | 1000 | Acceptance | Pilot testing, technical expertise acquisition.
R1.4 | Cybersecurity Threats | Cyberattacks or data breaches | Moderate - High | 3 | 35% | Throughout | Yes | 30000 | 10500 | Risk Transfer | Robust cybersecurity measures, cyber insurance.
R1.5 | Budget Overruns | Exceeding allocated budget | Moderate - High | 3 | 40% | Late-project | Yes | 25000 | 10000 | Mitigation | Careful budget monitoring, proactive cost control measures.
R1.6 | Quality Issues | High bug rate in code | Moderate - High | 3 | 40% | Throughout | Yes | 18000 | 7200 | Contingency | Rigorous testing and QA processes, code review practices.
Budget Contingency Reserve
Key Terms | [6 empty] | Over all Budget risk | 43200
Basics
Risk # | Add "R" to WBS #
Risk Name | Short name for the risk
Risk Statement | Because of <one or more causes>, <this risk event> might occur, resulting in <impact.>
Response Plan | What steps will the project take if / when the risk occurs? Some response plans need separate documentation. If so, refer to the document name as a cross reference.
Risk Strategies
Avoid | Eliminate scope to eliminate risk
Transfer | Transfer responsibility and impact to a third party
Mitigate | Amend project plans to lower the risk.
Accept | Live with the risk because there's little you can do to eliminate or manage it
Risk Expected Monetary Value
Likelihood | What % is the likelihood of the risk happening? Determined after quantitative analysis.
Impact | What is the dollar amount of the impact? Determined after quantitative analysis and response planning.
Risk EMV | = Likelihood * Impact
Use contingency reserves to cover EMV
Schedule Risk
Likelihood | What % is the likelihood of the risk happening? Determined after quantitative analysis.
Impact | What is the impact on time? Determined after quantitative analysis and response planning.
Schedule Risk | = Likelihood * Impact
Use schedule buffers, resource management, scope reduction to mitigate schedule risks
Create Contingency Budget
Calculate the EMV for each individual risk
Sum EVM for all risks to define overall budget risk
Set aside contingency reserve = overall budget risk
Map contingency reserve amount to budget overview
Final Step
Update your gantt chart, schedule, budget, and resource plans as needed to reflect the cost of mitigating risks

## Quality Management Planning
Quality Imperatives -- Use as Planning Prompts | Quality Planning Prompts | Activity | Project Phase | Resource | Start | Finish | Duration or Frequency | Comment
Integrate PQM | During initiation: | Define Problem | Initiation | Quality Control Lead
Define, manage, and integrate PQM processes. | Identify user needs. | Align with organizational goal and strategy | Initiation | Quality Control Lead
Integrate PQM with other project plans and activities. | Define the problem or opportunity. | Define, manage, and integrate PQM processes | Planning | Quality Control Lead
Integrate PQM with organizational quality management. | Align with organizational strategy. | Create a quality management mindset | Planning | Quality Control Lead
Promote a quality management mindset and culture. | Define intended benefits. | Define and execute quality assurance procedures | Planning | Quality Control Team
Identify and Satisfy User Needs | Conduct a stakeholder analysis. | Assign QA tasks to appropriate resources | Planning | Quality Control Lead
Define and perform quality assurance processes. | Conduct a requirements analysis. | Create budget for the cost of quality | Planning | Quality Control Lead
Define and perform usability testing. | Address the needs of the end user. | Define quality escalation process | Planning | Quality Control Lead
Validate deliverables against acceptance criteria. | During planning: | Define quality related reporting | Planning | Quality Control Lead
Define and perform user acceptance testing. | Define appropriate PQM activities. | Update the quality-related risk registry. | Planning | Quality Control Lead
Deliver Outputs that Conform with Specifications | Assign them to appropriate resources. | Create test cases | Execution | Quality Analyst
Define testing and control activities. | Add the activities to the schedule. | Automate Test Cases | Execution | Automation Engineer
Identify and manage defects. | Budget for the cost of quality. | Execute System Testing | Execution | Quality Analyst
Verify deliverables against specifications. | Update risk register re. quality-related risks. | Execute Load Testing | Execution | Quality Analyst
Comply with Standards and Regulations | Determine quality-related reporting and communication. | Execute Regression Testing | Execution | Quality Analyst
Identify relevant standards and regulations. | Define quality-related escalation processes. | User Acceptance Testing | Execution | Quality Analyst
Define and perform quality compliance activities. | During execution and control: | Defect creation and tracking | Execution | Quality Analyst
Document, monitor, and audit compliance activities. | Facilitate and monitor PQM Performance | Check for specification compliance | Closure | Quality Control Team
Improve compliance and compliance processes. | Take corrective actions when results vary from plans. | Suggest enhancements to existing processes | Closure | Quality Control Team
Optimize PM and PQM Processes | Continuously improving quality management. | Review of QA Metrics and Reports | Closure | Quality Control Lead
Monitor quality management processes. | During closure: | Documentation Review | Closure | Quality Control Team
Continually improve quality management. | Validate that deliverables satisfy user needs.
Monitor project management processes. | Verify conformance to specifications.
Continually improve project management processes. | Confirm compliance with standards and regulations.
Eliminate waste. | Recommend improvements to existing processes.
Add value.
How to use this template
Work with your quality management experts to develop your quality management plan
Use both sets of prompts to identify and plan quality management activities
Add quality management resources to your resource requirements
Create 3 point duration and cost estimates
Update schedule
Update risk register
Update other impacted project documents
Communicate the change
If desired, you can modify this to be a quality register for tracking purposes during execution

## Communications Planning
Communications Planning
This table can help you plann project communications and engagement for each phase of the project
Project Initiation
Activity | Audiences | Formats | Outputs
Define problem or opportunity | Sponsors Key stakeholders | Sponsor and stakeholder meetings Steering committee | Problem and opportunity statement
Identify stakeholders | Sponsors Key stakeholders SMEs End users | Sponsor and stakeholder meetings Steering committee Workshops Surveys | Power - Interest Grid RACI matrix Stakeholder map Stakeholder register
Identify and document requirements | Sponsors Key stakeholders SMEs End users Business Analyst | Sponsor and stakeholder meetings Steering committee Workshops Surveys | Use cases User stories Business Requirements Document (BRD)
Approve project scope | Sponsors Key stakeholders | Sponsor and stakeholder meetings Steering committee Gate review | Approved project scope statement
Approve project charter | Sponsors Key stakeholders | Sponsor and stakeholder meetings Workshops Steering committee Gate review | Approved project charter
Project Planning
Activity | Audiences | Formats | Outputs
Plan project planning | Sponsors Key stakeholders | Sponsor and stakeholder meetings | Project content management strategy Project planning requirements document
Create subsidiary plans | Sponsors Key stakeholders SMEs End users | Workshops | WBS Resource plan Activity list and Gantt chart Schedule Budget Risk management plan Quality management plan Communications plan Procurement plan Stakeholder management plan
Approve project plans | Sponsors Key stakeholders | Sponsor and stakeholder meetings Steering committee Gate review | Approved project plan
Project Execution and Control
Activity | Audiences | Formats | Outputs
Report status | Sponsor Key stakeholders Project teams | Sponsor and stakeholder meetings Steering committees Team meetings Status requests | Activity list updates Slide decks or equivalents Newsletters Email
Maintain stakeholder alignment | Sponsor Key stakeholders | Sponsor and stakeholder meetings Steering committees | Stakeholder register updates Change requests
Control project change - Corrective actions - Approved changes | Sponsor Key stakeholders Project teams | Change control meetings | Change requests Change log Updated project documentation
Project Closure
Activity | Audiences | Formats | Outputs
Acccept deliverables | Sponsor Key stakeholders Project teams | Check lists Sponsor and stakeholder meetings Team meetings Supplier engagement | Formal signoff Email acceptance Completed checklists Updated activity list Archived project deliverables
Conduct lessons learned | Sponsor Key stakeholders Project teams | Workshops | Lessons learned documentation Updated process assets and tools Additions to project archive

## Sample File Directory
Key Documents | Purpose | Doc Type | Access Rights | Comments
Project Charter | - Document problem and opportunity statement - Document project scope and deliverables - Exclude what is out of scope - Identify relevant compliance standards - Define high-level schedule and budget - Indicate key risks - Define roles and responsibilities | PDF | Edit - PM
Requirements Trace Matrix | - Document how requirements are elaborated and managed from initiation through closing - Link to relevant documents | Spreadsheet | Edit - PM and quality management leads
Business Requirements Document | Document project business requirements, including - How they link to problem or opportunity statement - Scope definition - Acceptance criteria - KPIs - Impacted workstreams | PDF | Edit - PM and business analysts | - Sometimes this will include wireframes, security requirements, data requirements - Sometimes there is a BRD for each workstream instead of a master BRD
Change Requests Folder | Purpose | Doc Type | Access Rights | Comments
Change Requests | Well-defined document to request significant project changes | Word doc or spreadhseet | Edit - PM | This should also indicated the ultimate decision and link to relevant documents
Tracking Tools | Purpose | Doc Type | Access Rights | Comments
Activity List and Gantt Chart | - Document and manage project activities - Indicate progress - Visualize schedule as Gantt Chart | Spreadsheet MS Project Smartsheet | Edit - PM
Project Budget | Document and manage project updates | Spreadsheet | Edit - PM View - Only sponsor and others indicated | Keep this private or in a separate place
Tracking Spreadsheet
Action Items | Create log to track action items |  | Edit - PM | - Unless necessary, have one master spreadsheet for the entire project - Use filters so people can view what matters to them
Risk Register | Create log to track risk management info
Issue Log | Create log to track issue management
Decision Log | Document project decisions
Project Status | Purpose | Doc Type | Access Rights | Comments
Status Reports Folder
Executive updates | Dashboard for executives and sponsors Decision requests Issue, risk, and decision log | PPT or other | Edit - PM View - Execs, sponsor, steering committee
Consolidated status report | General status report for all stakeholders | PPT or other | Edit - PM | Some teams use PPT Some use a central "dashboard" tool such as Smartsheet
Meeting Notes
Sponsor and Steering Committee | Meeting agenda Review and update tracking spreadsheet Capture action items Update tracking spreadsheet | Word or Slide Deck | Edit - PM View - Only sponsor and steering committee members | Can have a single doc and just update it week by week Or have a separate doc each week
Workstream Team 1 | same |  | Edit - PM | Some teams prefer to keep meeting notes in workstream folders
Workstream Team 2 | same |  | Edit - PM
Workstream Team 3 etc. | same |  | Edit - PM
Edit - PM
Workstream Folders | Purpose | Doc Type | Access Rights | Comments
Primary folder for each workstream | Store all documents related to workstream - Designs - Specifications - Deliverables - Quality management documents |  | Depends on project | - Some of these documents may be placed in doc control, source control, or other systems - Bug tracking may be in a separate system too

## Change Control Workflow
Cha